## Years 1-5
Bid Form Cost Proposal-Schedule of Deliverables RFP-18-013
ACTIVITY | MONTH / YEAR | TOTAL COST
Year 1 6/1/18 to 5/31/19
Commission passages and items for 2019 field tests | 2018-06-01 | 0
Arrange for an independent party with demonstrated expertise in high-quality, large-scale assessment to conduct, at the Contractor’s sole cost, an alignment study | June-Sept 2018 | 0
Conduct Passage and Item review meeting with NYS educators for 2019 field tests | July-Aug 2018 | 0
Develop a sample item booklet for each grade band and modality of the current NYSESLAT test design using items administered in previous years' tests | 2018-10-01 | 0
Select schools for 2019 field tests | Oct-Nov 2018 | 0
Prepare school administrator's manual for 2019 operational tests | Oct-Dec 2018 | 0
Prepare and send notification to selected schools for 2019 field tests | Nov-Dec 2018 | 0
Process 2019 field test enrollments and develop and print packing lists (manifests) to pick and pack materials | Nov-Dec 2018 | 0
Prepare final copies of 2019 field test forms | Nov-Dec 2018 | 0
Conduct final eyes review with NYS educators for 2019 field tests | Nov-Dec 2018 | 0
Prepare 2019 field test teacher directions and administration materials | Nov-Dec 2018 | 0
Process 2019 operational test orders, supplemental requests, and pick and pack materials | Nov 2018-Jan 2019 | 0
Maintain customer service helpline for 2019 exam ordering and pre-administration | Nov 2018-Apr 2019 | 0
Print and duplicate all 2019 field tests and related materials | Dec 2018-Jan 2019 | 0
Conduct 1 in-person and 1 webinar to train RBERN and large city scoring trainers for scoring the 2019 operational speaking and writing tests | 2019-01-01 | 0
Ship 2019 field test forms and related materials | Jan-Feb 2019 | 0
Administer 2019 field tests | Feb-Mar 2019 | 0
Print 2019 operational test forms and related materials | Feb-Mar 2019 | 0
Print and Reproduce 2019 operational test scoring materials for Speaking and Writing | 2019-03-01 | 0
Print 2019 operational tests braille and large-type editions | 2019-03-01 | 0
Process returned 2019 field test materials and contact schools with outstanding materials | Mar-Apr 2019 | 0
Commission passages and items for 2020 field tests | Mar-Apr 2019 | 0
Ship 2019 operational test braille and large-type editions as requested by schools | Mar-May 2019 | 0
Ship 2019 operational test forms and related materials | Mar-May 2019 | 0
Ship 2019 operational test scoring materials for Speaking and Writing | Apr-May 2019 | 0
Maintain customer service helpline for 2019 administration and scoring periods | Apr-June 2019 | 0
Process returned 2019 operational tests and contact schools with outstanding materials | Apr-June 2019 | 0
Conduct Item prototyping and test specifications development with NYS educators for revised NYSESLAT | Apr-July 2019 | 0
Receive raw score data file for 2019 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2019 | 0
Scaling/equating and psychometric analysis of 2019 operational tests | May-June 2019 | 0
TOTAL YEAR 1 |  | 0
Year 2 6/1/19 to 5/31/20
Conduct Rangefinding with NYS educators for scoring 2019 speaking and writing field tests | June-July 2019 | 0
Deliver general research file to NYSED for 2019 operational tests | June-July 2019 | 0
Conduct Passage and Item review meeting with NYS educators for 2020 field tests | June-July 2019 | 0
Score 2019 NYSESLAT field tests (MC and CR items) | 2019-07-01 | 0
Conduct rescoring of 10% of locally scored 2019 operational test speaking and writing responses | Aug-Sept 2019 | 0
Provide technical report on 2019 NYSESLAT field tests | Sept-19 | 0
Conduct forms construction meeting with NYS educators for 2020 operational tests | Oct-Nov 2019 | 0
Conduct meeting with NYS educators to develop performance level descriptors for revised NYSESLAT | Oct-Nov 2019 | 0
Select schools for 2020 field tests | Oct-Nov 2019 | 0
Prepare directions for administration and school administrator's manual for 2020 operational tests | Oct-Dec 2019 | 0
Prepare final copies of 2020 field test forms | Nov-Dec 2019 | 0
Prepare and send notification to selected schools for 2020 field tests | Nov-Dec 2019 | 0
Process 2020 field test enrollments and develop and print packing lists (manifests) to pick and pack material | Nov-Dec 2019 | 0
Prepare 2020 field test directions for administration and other administration materials | Nov-Dec 2019 | 0
Conduct final eyes review with NYS educators for 2020 field tests | Nov-Dec 2019 | 0
Provide technical report on 2019 operational tests | Nov-Dec 2019 | 0
Process 2020 operational test orders, supplemental requests, and pick and pack materials | Nov 2019-Jan 2020 | 0
Maintain customer service helpline for 2020 exam ordering and pre-administration | Nov 2019-Apr 2020 | 0
Print and duplicate all 2020 field tests and related materials | Dec 2019-Jan 2020 | 0
Conduct final eyes review with NYS educators for 2020 operational tests | 2019-12-01 | 0
Conduct 1 in-person session and 1 webinar to train RBERN and large city scoring trainers for scoring the 2020 operational speaking and writing tests | 2020-01-01 | 0
Prepare final copies of the 2020 operational test forms | Jan-Feb 2020 | 0
Ship 2020 NYSESLAT field tests and related materials | Jan-Feb 2020 | 0
Administer 2020 field tests | Feb-Mar 2020 | 0
Develop 2020 operational test scoring materials for Speaking and Writing | 2020-02-01 | 0
Prepare 2020 operational test large-type and braille forms | 2020-02-01 | 0
Print 2020 operational test forms and related materials | Feb-Mar 2020 | 0
Print and Reproduce 2020 operational test scoring materials for Speaking and Writing | 2020-03-01 | 0
Print 2020 operational tests braille and large-type editions | 2020-03-01 | 0
Process returned 2020 field test materials and contact schools with outstanding materials | Mar-Apr 2020 | 0
Commission passages for 2021 field tests | Mar-Apr 2020 | 0
Ship 2020 operational test forms and related materials | Mar-May 2020 | 0
Ship 2020 operational test braille and large-type editions as requested by schools | Mar-May 2020 | 0
Ship 2020 operational test scoring materials for Speaking and Writing | Apr-May 2020 | 0
Process returned 2020 operational tests and contact schools with outstanding materials | Apr-June 2020 | 0
Maintain customer service helpline for 2020 administration and scoring periods | Apr-June 2020 | 0
Receive raw score data file for 2020 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2020 | 0
Scaling/equating and psychometric analysis of 2020 operational tests | May-June 2020 | 0
Conduct item prototyping/test specifications development meeting with NYS educators for new kindergarten entry initial identification test | May-July 2020 | 0
TOTAL YEAR 2 |  | 0
Year 3 6/1/20 to 5/31/21
Conduct Rangefinding with NYS educators for scoring 2020 Speaking and Writing field tests | June-July 2020 | 0
Deliver general research file to NYSED for 2020 operational tests | June-July 2020 | 0
Conduct Passage and Item review meeting with NYS educators for 2021 NYSESLAT field tests | June-July 2020 | 0
Score 2020 NYSESLAT field tests (MC and CR items) | 2020-07-01 | 0
Develop stimuli and items for the new Kindergarten Entry initial identification field tests | July-Aug 2020 | 0
In the event that students are participating in the NYSESLAT field testing through two modes, CBT and PBT, conduct comparability study of CBT vs. PBT and prepare report | Aug-Sept 2020 | 0
Conduct rescoring of 10% of locally scored 2020 operational test speaking and writing responses | Aug-Sept 2020 | 0
Provide technical report on 2020 NYSESLAT field tests | Sept-20 | 0
Conduct forms construction meeting with NYS educators for 2021 operational tests | Oct-Nov 2020 | 0
Select schools for 2021 field tests | Oct-Nov 2020 | 0
Prepare directions for administration and school administrator's manual for 2021 operational tests | Oct-Dec 2020 | 0
Prepare final copies of 2021 field test forms | Nov-Dec 2020 | 0
Prepare and send notification to selected schools for 2021 field tests | Nov-Dec 2020 | 0
Process 2021 field test enrollments and develop and print packing lists (manifests) to pick and pack material | Nov-Dec 2020 | 0
Prepare 2021 field test directions for administration and other administration materials | Nov-Dec 2020 | 0
Conduct final eyes review with NYS educators for 2021 field tests | Nov-Dec 2020 | 0
Provide technical report on 2020 operational tests | Nov-Dec 2020 | 0
Process 2021 operational test orders, supplemental requests, and pick and pack materials | Nov 2020-Jan 2021 | 0
Maintain customer service helpline for 2021 exam ordering and pre-administration | Nov 2020-Apr 2021 | 0
Conduct final eyes review with NYS educators for 2021 operational tests | 2020-12-01 | 0
Print and duplicate all 2021 field tests and related materials | Dec 2020-Jan 2021 | 0
Conduct 1 in-person session and 1 webinar to train RBERN and large city scoring trainers for scoring the 2021 operational speaking and writing tests | 2021-01-01 | 0
Conduct stimuli/item review meeting with NYS educators for the new kindergarten entry initial identification field test | 2021-01-01 | 0
Prepare final copies of the 2021 operational test forms | Jan-Feb 2021 | 0
Ship 2021 NYSESLAT field tests and related materials | Jan-Feb 2021 | 0
Develop 2021 operational test scoring materials for Speaking and Writing | 2021-02-01 | 0
Prepare 2021 operational test large-type and braille forms | 2021-02-01 | 0
Administer 2021 field tests | Feb-Mar 2021 | 0
Print 2021 operational test forms and related materials | Feb-Mar 2021 | 0
Print and Reproduce 2021 operational test scoring materials for Speaking and Writing | 2021-03-01 | 0
Print 2021 operational tests braille and large-type editions | Mar-Apr 2021 | 0
Process returned 2021 field test materials and contact schools with outstanding materials | Mar-Apr 2021 | 0
Commission passages and items for 2022 field tests | Mar-Apr 2021 | 0
Ship 2021 operational test forms and related materials | Mar-May 2021 | 0
Ship 2021 operational test braille and large-type editions as requested by schools | Mar-May 2021 | 0
Ship 2021 operational test scoring materials for Speaking and Writing | Apr-May 2021 | 0
Maintain customer service helpline for 2021 administration and scoring periods | Apr-June 2021 | 0
Process returned 2021 operational tests and contact schools with outstanding materials | Apr-June 2021 | 0
Receive raw score data file for 2021 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2021 | 0
Scaling/equating and psychometric analysis of 2021 operational tests | May-June 2021 | 0
TOTAL YEAR 3 |  | 0
Year 4 6/1/21 to 5/31/22
Conduct rangefinding with NYS educators for scoring 2021 Speaking and Writing field tests | June-July 2021 | 0
Deliver general research file to NYSED for 2021 operational tests | June-July 2021 | 0
Conduct Passage and Item review meeting with NYS educators for 2022 field tests | June-July 2021 | 0
In the event that students are participating in the NYSESLAT field testing and/or operational testing through two modes, CBT and PBT, conduct comparability studies of CBT vs. PBT and prepare report(s) | June-Aug 2021 | 0
Score 2021 NYSESLAT field tests (MC and CR items) | July-21 | 0
Conduct rescoring of 10% of locally scored 2021 operational test speaking and writing responses | Aug-Sept 2021 | 0
Arrange for an independent party with demonstrated expertise in high-quality, large-scale assessment to conduct, at the Contractor’s sole cost, an alignment study | Aug-Oct 2021 | 0
Develop a sample item booklet for each grade band and modality for the new NYSESLAT operational tests based upon the new NYS Next Generation ELA Standards | Sept-21 | 0
Provide technical report on 2021 NYSESLAT field tests | Sept-21 | 0
Develop, translate, print, and distribute to schools a parent brochure on the new operational NYSESLAT tests based on new NYS Next Generation ELA standards | Oct-Nov 2021 | 0
Conduct forms construction meeting with NYS educators for 2022 operational tests | Oct-Nov 2021 | 0
Select schools for 2022 field tests | Oct-Nov 2021 | 0
Prepare directions for administration and school administrator's manual for 2022 operational tests | Oct-Dec 2021 | 0
Prepare 2022 field test directions for administration and other administration materials | Nov-Dec 2021 | 0
Prepare final copies of 2022 field test forms | Nov-Dec 2021 | 0
Prepare and send notification to selected schools for 2022 field tests | Nov-Dec 2021 | 0
Process 2022 field test enrollments and develop and print packing lists (manifests) to pick and pack material | Nov-Dec 2021 | 0
Provide technical report on 2021 operational tests | Nov-Dec 2021 | 0
Conduct final eyes review with NYS educators for 2022 operational tests | Nov-Dec 2021 | 0
Process 2022 operational test orders, supplemental requests, and pick and pack materials | Nov 2021-Jan 2022 | 0
Maintain customer service helpline for 2022 exam ordering and pre-administration | Nov 2021-Apr 2022 | 0
Conduct final eyes review with NYS educators for 2022 field tests | 2021-12-01 | 0
Print and duplicate all 2022 field tests and related materials | Dec 2021 - Jan 2022 | 0
Conduct turn-key scoring training in 12 regional locations for the first administration of operational tests aligned to the new NYS Next Generation ELA Standards | Jan-Feb 2022 | 0
Prepare final copies of the 2022 operational test forms | Jan-Feb 2022 | 0
Ship 2022 field tests and related materials | Jan-Feb 2022 | 0
Develop 2022 operational test scoring materials for Speaking and Writing | 2022-02-01 | 0
Prepare 2022 operational test large-type and braille forms | 2022-02-01 | 0
Administer 2022 field tests | Feb-Mar 2022 | 0
Print 2022 operational test forms and related materials | Feb-Mar 2022 | 0
Conduct final eyes review with NYS educators of the new Entry Kindergarten initial identification field tests | 2022-03-01 | 0
Print and Reproduce 2022 operational test scoring materials for Speaking and Writing | 2022-03-01 | 0
Process returned 2022 field test materials and contact schools with outstanding materials | 2022-03-01 | 0
Print 2022 operational tests braille and large-type editions | 2022-03-01 | 0
Commission passages and items for 2023 field tests | Mar-Apr 2022 | 0
Ship 2022 operational test forms and related materials | Mar-May 2022 | 0
Ship 2022 operational test braille and large-type editions as requested by schools | Mar-May 2022 | 0
Print and duplicate new Kindergarten entry initial identification field tests based upon new NYS Next Generation ELA standards | 2022-04-01 | 0
Ship 2022 operational test scoring materials for Speaking and Writing | Apr-May 2022 | 0
Process returned 2022 operational tests and contact schools with outstanding materials | Apr-June 2022 | 0
Maintain customer service helpline for 2022 administration and scoring periods | Apr-June 2022 | 0
Ship new Kindergarten entry initial identification field tests to schools | 2022-05-01 | 0
Receive raw score data file for 2022 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2022 | 0
Scaling/equating and psychometric analysis of 2022 operational tests | May-June 2022 | 0
TOTAL YEAR 4 |  | 0
Year 5 6/1/22 to 12/31/22
Conduct Rangefinding with NYS educators for scoring 2022 speaking and writing field tests | June-July 2022 | 0
Deliver general research file to NYSED for 2022 operational tests | June-July 2022 | 0
Conduct Passage and Item review meeting with NYS educators for 2023 field tests | June-July 2022 | 0
Conduct standard setting with NYS educators for NYSESLAT and provide technical report | June-July 2022 | 0
In the event that students are participating in the NYSESLAT field testing and/or operational testing through two modes, CBT and PBT, conduct comparability studies of PBT vs. CBT and prepare report(s) | June-July 2022 | 0
Administer new Kindergarten entry initial identification field tests based upon new NYS Next Generation ELA standards | June-Sept 2022 | 0
Score 2022 NYSESLAT field tests (MC and CR items) | 2022-07-01 | 0
Conduct rescoring of 10% of locally scored 2022 operational test speaking and writing responses | Aug-Sept 2022 | 0
Provide technical report on 2022 field tests | Sept-22 | 0
Score new Kindergarten entry initial identification field tests | 2022-10-01 | 0
Provide technical report on 2022 operational tests | Nov-Dec 2022 | 0
TOTAL YEAR 5 |  | 0

## Summary
Budget Form –Cost Proposal
New York State Education Department
Request for Proposals 18-013
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Bidder Name:
Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Grand Total
0 | 0 | 0 | 0 | 0 | 0
The Financial Criteria portion of the RFP will be scored based upon the grand total cost.
Vendors should be prepared to show how they derived the amounts for each activity should they be subject to audit by NYSED or Office of the State Comptroller.
Vendor Signature: |  |  | Date:
Printed Name:
Company Name:
Company Address:

## Subcontracting
Request for Proposals 18-013
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Subcontracting Form
Bidder Name:
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise.
Leave box blank if subcontractor is neither.
**Subcontracting is limited to thirty percent (30%) of the total contract budget.

## MWBE Purchases
Request for Proposals 18-013
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
MWBE Purchases Form
Bidder Name:
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!